TEAM DETAILS

Team members = 4
Sprint capacity = 15–25 story points

RELEASE 1 — MVP

Goal:

User can search movie → select show → choose seats → pay → book ticket

Workflow:

Login → Search movie → Select city → Select theatre → Select showtime → Enter ticket count → Seat selection → Payment → Booking confirmation

Sprint 1 – Authentication & Movie Setup

Epics: Authentication, Movie Management

EP01 – User Authentication

| Story | Points |
| --- | --- |
| UAUS001 Register account | 3 |
| UAUS002 Login | 2 |
| UAUS003 Guest access | 1 |
| UAUS004 Validate user | 2 |
| UAUS006 Admin login | 2 |

Subtotal = 10

EP03 – Movie Management

| Story | Points |
| --- | --- |
| MMUS001 Add movie | 3 |
| MMUS002 Enter movie details | 2 |
| MMUS007 View movie list | 2 |

Subtotal = 7

Sprint 1 Total

17 Story Points

Goal:

Admin can add movies and users can login

Sprint 2 – Movie Discovery & Show Selection

Epics: Movie Search, Show Selection

EP04 – Movie Search

| Story | Points |
| --- | --- |
| MSUS001 Search by title | 2 |
| MSUS002 Search by language | 2 |

Subtotal = 4

EP05 – Show Selection

| Story | Points |
| --- | --- |
| SUS001 Select city | 1 |
| SUS002 Select theatre | 2 |
| SUS003 Select movie in theatre | 2 |
| SUS004 Select showtime | 2 |

Subtotal = 7

EP07 – Ticket Booking

| Story | Points |
| --- | --- |
| TBUS001 Enter number of tickets | 2 |
| TBUS002 Validate ticket quantity | 1 |

Subtotal = 3

Sprint 2 Total

14 Story Points

Goal:

User can search movies and start booking

Sprint 3 – Seat Selection

Epic: Seat Selection

| Story | Points |
| --- | --- |
| SSUS001 Seat layout | 3 |
| SSUS002 Available seats | 2 |
| SSUS003 Show booked seats | 1 |
| SSUS004 Select seat | 2 |
| SSUS005 Select multiple seats | 2 |
| SSUS009 Send seat details to booking | 1 |

Subtotal = 11

EP07 – Ticket Booking

| Story | Points |
| --- | --- |
| TBUS003 Validate seat selection | 2 |
| TBUS004 View booking details | 1 |

Subtotal = 3

Sprint 3 Total

14 Story Points

Goal:

User can select seats and review booking

Sprint 4 – Payment & Booking Confirmation

Epics: Payment, Booking

EP08 – Payment Processing

| Story | Points |
| --- | --- |
| USPP001 Make payment | 2 |
| USPP002 Card payment | 3 |
| USPP005 Payment confirmation | 1 |

Subtotal = 6

EP07 – Ticket Booking

| Story | Points |
| --- | --- |
| TBUS005 Validate payment status | 3 |
| TBUS007 Update seat status | 3 |
| TBUS006 View final booking details | 1 |

Subtotal = 7

Sprint 4 Total

13 Story Points

Goal:

User can pay and confirm ticket booking

MVP COMPLETED

User can:

- Register / Login

- Admin login and add movies

- Search movie

- Select city

- Select theatre

- Select showtime

- Enter ticket count

- Select seats

- Make payment

- Book ticket

RELEASE 2 – User Experience Improvements

Sprint 5

Epics: User Management, Movie Search

EP02 – User Management

| Story | Points |
| --- | --- |
| UMUS003 View profile | 2 |
| UMUS004 Update profile | 2 |
| UMUS002 View user accounts | 2 |

Subtotal = 6

EP04 – Movie Search

| Story | Points |
| --- | --- |
| MSUS003 Search by genre | 2 |
| MSUS004 Search by theatre | 3 |
| MSUS005 Search by city | 3 |

Subtotal = 8

Sprint 5 Total

14 Story Points

Goal:

Improve user profile and movie search

Sprint 6

Epics: Seat Selection, User Management

EP06 – Seat Selection

| Story | Points |
| --- | --- |
| SSUS006 View selected seats | 1 |
| SSUS007 Modify seat selection | 2 |
| SSUS008 Remove selected seats | 1 |

Subtotal = 4

EP02 – User Management

| Story | Points |
| --- | --- |
| UMUS001 Create officer account | 3 |
| UMUS008 Update officer account | 2 |
| UMUS006 Deactivate user | 2 |

Subtotal = 7

Sprint 6 Total

11 Story Points

Goal:

Improve seat management and user administration

RELEASE 3 – Ticket Cancellation & Refund

Sprint 7

EP09 – Ticket Cancellation

| Story | Points |
| --- | --- |
| TCUS001 Cancel ticket | 3 |
| TCUS002 Update seat availability | 2 |
| TCUS004 Cancellation confirmation | 1 |

Subtotal = 6

EP08 – Payment

| Story | Points |
| --- | --- |
| USPP004 Cash payment | 2 |

Subtotal = 2

Sprint 7 Total

8 Story Points

Goal:

Allow ticket cancellation

Sprint 8

EP09 – Ticket Cancellation

| Story | Points |
| --- | --- |
| TCUS003 Officer cancel ticket | 2 |
| TCUS005 Refund ticket | 3 |
| TCUS006 Update refund transaction | 2 |

Subtotal = 7

RELEASE 4 – Reports

Sprint 9

EP10 – Report Management

| Story | Points |
| --- | --- |
| RMUS001 Movie report | 2 |
| RMUS002 Booking report | 2 |
| RMUS003 Customer report | 3 |

Total = 7

Sprint 10

EP10 – Report Management

| Story | Points |
| --- | --- |
| RMUS004 Daily booking report | 3 |
| RMUS005 Cancellation report | 2 |

Total = 5

Final Sprint Overview

| Sprint | Points | Release |
| --- | --- | --- |
| Sprint 1 | 17 | MVP |
| Sprint 2 | 14 | MVP |
| Sprint 3 | 14 | MVP |
| Sprint 4 | 13 | MVP |
| Sprint 5 | 14 | Release 2 |
| Sprint 6 | 11 | Release 2 |
| Sprint 7 | 8 | Release 3 |
| Sprint 8 | 7 | Release 3 |
| Sprint 9 | 7 | Release 4 |
| Sprint 10 | 5 | Release 4 |